## Sprint 2 Daily SCRUM Standup
Question | Team Member | Week: 2/10/2025-2/17/2025 | [6 empty] | Week: 2/17/2025-2/24/205
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Hannah | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the Sprint 1 Review with Dr. Bowman and our fellow classmates. | Yesterday, Hannah made good progress on Sprint 2's PSPI. | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah made good progress on Sprint 2's PSPI. |  |  | Yesterday, we enjoyed time with our familes for the weekend. Our group opts to work on this project Monday thru Friday to allow for time during the weekends for family and other courses. | Yesterday, we attended the Sprint 1 Review with Dr. Bowman and our fellow classmates. | Yesterday, Hannah continued work on the Narrative and Conclusions of the Executive Summary | Yesterday we attended our weekly team meeting. During the meeting we checked all backlog items, assigned work, and scheduled timelines for committed items. We also made a final decison on DB provider for the project. | Yesterday, Hannah completed the Sprint 2 PSPI
| Heather |  |  | Yesterday, Heather made good progess on the non-functional project requirements. |  | Yesterday, Heather made good progess on the project backlog. |  |  |  |  | Yesterday, Heather worked on the SCRUM meeting log. |  | Yesterday, Heather completed the Non-functional requirements.
| Lauren |  |  | Yesterday, Lauren made good progress on the Sprint 2 SR&R Presentation. |  | Yesterday, Lauren completed the updated context diagram. |  |  |  |  | Yesterday, Lauren worked on the Use Case Diagram. |  | Yesterday, Lauren finalized the Sprint 2 presentation
What will you work on today? | Hannah | Today we will all attend the Sprint 1 Review with Dr. Bowman and our fellow classmates. | Today, Hannah will work on Sprint 2's PSPI. | Today we will attend our weekly team meeting. During the meeting we will check review all backlog items, assign work, and schedule timelines for committed items. | Today, Hannah will continue work on Sprint 2's PSPI. | Today, Hannah will work on the Narrative and Conclusions of the Executive Summary |  |  | Today we will all attend Dr. Bowman's WebEx with our fellow classmates. | Today, Hannah will continue work on the Narrative and Conclusions of the Executive Summary | Today we will attend our weekly team meeting. During the meeting we will check in on Sprint progress, swarm on any unfinished tasks as needed, and complete the Sprint Review document as a team. | Today, Hannah will continue work on the Sprint 2 PSPI | Today we will work on finalizing all project deliverables, reviewing each other's work as quality control, and uploading/validating all docs are in GitHub.
| Heather |  | Today, Heather will work on the non-functional project requirements. |  | Today, Heather will work on the project backlog. | Today, Heather will work on the project burn down chart. |  |  |  | Today, Heather will work on the SCRUM meeting log. |  | Today, Heather will work completing the Non-functional requirements.
| Lauren |  | Today, Lauren will work on the Sprint 2 SR&R Presentation. |  | Today, Lauren will work on the updated context diagram | Today, Lauren finish the PPT slides for Sprint 2. |  |  |  | Today, Lauren will work on the Use Case Diagram. |  | Today, Lauren will finalize the Sprint 2 presentation
Do you have any obstacles? | Hannah | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. |  |  | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today. | No one reported any obstacles today.
Heather
Lauren

## Sprint 1 Daily SCRUM Standup
Question | Team Member | Week: 1/27/2025-2/3/2025 | [6 empty] | Week: 2/3/2025-2/10/2025
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Hannah |  | Company background | Group meeting |  |  |  |  | Gather photos |  | Fix team contract | Group Meeting
| Heather | Sprint backlog | Class meeting | Group meeting | organizing documentation | powerpoint |  |  | finalizing documentation |  | Group Meeting
| Lauren |  | Class meeting | Group Meeting | Site cost research | Requirments and constraints |  | Use case and context diagrams |  | Final draft template and logo & Class meeting |  | Group Meeting
What will you work on today? | Hannah | Company background | Problem analysis |  |  |  |  | Gather photos | class meeting | Fix team contract | Group Meeting
| Heather | Burndown charts | Sprint backlog | refining team member assignments | organizing documentation | powerpoint |  |  | class meeting |  | Group Meeting
| Lauren | Class meeting | Group Meeting | Site cost research | Requirments and constraints |  | Use case and context diagrams |  | Class meeting |  | Group Meeting
Do you have any obstacles? | Hannah | no | no | no | no | no | no | no | no | no | no | no | no | no | no
| Heather | no | no | no | no | no | no | no | no | no | no | no | no | no | no
| Lauren | no | no | no | no | no | no | no | no | no | no | no | no | no | no

## Sprint 3 Daily SCRUM Standup
Question | Team Member | Week: 2/24/205-3/3/2025 | [6 empty] | Week: 3/3/2025-3/10/2025 | [6 empty] | Week: 3/10/2025-3/17/2025
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Hannah
Heather
Lauren
What will you work on today? | Hannah
Heather
Lauren
Do you have any obstacles? | Hannah
Heather
Lauren

## Sprint 4 Daily SCRUM Standup
Question | Team Member | Week: 3/17/2025-3/24/2025 | [6 empty] | Week: 3/24/2025-3/31/2025 | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Hannah
Heather
Lauren
What will you work on today? | Hannah
Heather
Lauren
Do you have any obstacles? | Hannah
Heather
Lauren

## Sprint 5 Daily SCRUM Standup
Question | Team Member | Week: 3/31/2025-4/7/2025 | [6 empty] | Week: 4/7/2025-4/14/2025
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Hannah
Heather
Lauren
What will you work on today? | Hannah
Heather
Lauren
Do you have any obstacles? | Hannah
Heather
Lauren

## Sprint 6 Daily SCRUM Standup
Question | Team Member | Week:4/14/2025-4/21/2025 | [6 empty] | Week:4/21/2025-4/28/2025
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Hannah
Heather
Lauren
What will you work on today? | Hannah
Heather
Lauren
Do you have any obstacles? | Hannah
Heather
Lauren